## Tender
Annexure - II
THE LAWRENCE SCHOOL , LOVEDALE
TENDER SCHEDULE
EOI No : EOI/LS/EM/GSR/603 Name of the work : Providing Galvalume sheet roofing over existing Madras Terrace at Senior School Vindhya Dorm prefect joint Last Date for Submission : 30.04.2021 before 3 pm Period of Completion : 30 Days
S.No | Category | Description of Items | Qty | Unit | Rate | Amount | Remarks
1 | Dismantling of Brick work | Dismantling brick masonry in cement mortar walls for placing 125mm*100mm wooden rafters and clearing away the debris with initial lead of 10 m and lift of 2 m and dispose of the same at specified location all as directed by Engineer In-charge. | 1.65 | Cum
2 | Wooden frame resizing | Fixing only of plain, solid, straight sal/teak wooden wrought, framed rebated on the solid, rounded or chamfered, put together with glue pinned at joints and also provided the truss, purlins,door & window frames etc., Note: 1. Old wooden frames will be supplied by the school. 2. Contractor has to re-size the scantlings to make rebates for fixing. | 4.15 | Cum
3 | Galvalume sheet Single layer | Supplying and fixing of SINGLE LAYER Galvalume roofing sheet of 0.47 mm thick TCT 300 Mpa 150 GSM colour coated sheets with polyester coating of approved colour on the top over the 5 microns primer and 5 microns back up epoxy coating at the bottom including valley gutter & ridges of 450mm overlap on either side, etc., Note: Measurement shall be of superficial area of roof laid, laps will not be measured separately.Sample and colour to be approved by the school authorities. Sheet Make - JSW / BHUSHAN | 78 | Sqm
4 | Ridges | Supply and fixing of 0.5 mm thick galvalume color coated plain sheet on the roof edge (Ridges) etc fixed with SDST Screws Sheet Make - JSW / BHUSHAN | 16 | Rmt
5 | PCC 1:2:4 | Material & Labour for Cement concrete type B-0, 1:2:4 (12.5 mm graded aggregate) as in floor finishes, coving, coping, Drains & plinth protection etc including finishing the surfaces even & smooth with using extra cement & pigments of approved quality & required form work etc., Cement Grade - PPC 53 Cement Make - ACC / ULTRATECH / CORAMANDAL / CHETTINAD / DALMIA / SANKAR | 1.65 | Cum
6 | Structural steel | Supply & erection of handrail using SHS Section, edges of the tubes shall be welded with MS Plate etc. Roof trusses (framed), trussed purlins crane gantries, rails and fastenings and heavy bracket framing (Beam, tee, angle channel or flat sections) including distance pieces, cleats etc. Make - JSW / APOLLO | 380 | Kgs
7 | Enamel painting | Material and labour for Two coats of synthetic enamel paint over a coat of Primer on wooden surfaces/steel surfaces including preparation of surfaces etc Make - Asian paints | 133.85 | Sqm
8 | Rain water gutter | Material and labour for fixing of 0.5 mm thick galvalume color coated plain sheet for rain water gutter with necessary MS L angle including painting of MS items Etc., Gutter Size: pls refer the drawing in the remarks column (6"+8") x 7" x (8"+1") with support of MS 'L' angle (25*25*5mm) support at every 1 meter interval. Note: Necessary scaffolding for fixing the gutter ht.10m from ground to be included in the rate Sheet Make - JSW / BHUSHAN | 70 | Rmt
9 | 110mm PVC Pipe | Supply and fixing of PVC pipes (of same colour of the main building external wall) single socketed, in any length with rubber ring joints laid in trenches or in floors bore of pipe 110 mm 6Kg per Cm2 pressure including Special like socket, elbow with door, tee and "Y" Junction etc. Make : Finolex or Supreme | 50 | Rmt
TOTAL
GST @ 18%
GRAND TOTAL
Signature of the Contractor
| Note: | * Any additional input/submissions / terms & conditions may be attached as enclosures to this quote. * Column F, G, H and row no 3 are editable